## 202501 RMReport
Agency | Mgt # | NARA Group # | NARA Transfer Request (TR) | Film Collection Name | Aircraft or Satellite | Earliest Year | Latest Year | # of Originals | 2nd Generation Original | Dupes of EROS Film | #Rolls Remaining in the lower-level archive | Number of rolls that we have not scanned and don't plan to scan because they are duplicates | # of Roll Records Shipped to NARA | Total Frames | Frames Scanned | Frames to be scanned | Percent Scanned | Est Months to complete scanning | Indexes Available | Frame Level Metadata | Roll Level Metadata | Browse Imagery | Geographic Coordinates | Untitled Frames | Number of color Rolls | Number of Rolls Boxed Up | Box Level Inventory completed | Boxes on Pallets | Boxes/ Pallets Shipped to NARA
1 | 4 | 57 | TR-0057-2023-0009 | U.S. Geological Survey: full truckload: 2,399 rolls | Aircraft | 1937 | 2014 | 7440 | 43 | 1945 | 9428 | 0 | 12443 | 2665771 | 2665771 | 0 | 100 | 0 |  | 2994466 |  | Yes | 1967024 | 334376 | 1776 |  |  |  |  | Geo-referencing is ongoing.
1 | 4 | 57 | TR-0057-2023-0010 | U.S. Geological Survey: remainder: 1,388 rolls | Aircraft | 1937 | 2014
H | 17 | 57 | TR-0057-2024-0016 | USGS - Agency H | Aircraft | 1937 | 2012 | 4430 | 291 | 63 | 4784 | 0 | 231 | 192660 | 164093 | 28567 | 85.1723 | 6 |  | 202930 |  | Yes | 55153 | 11283 | 284 |  |  |  |  | Michigan DNR film data entry is complete; scanning in progress
H | 47 | 57 | TR-0057-2024-0059 | USGS - Agency H - Intermountain | Aircraft | 1956 | 2002 | 9629 | 0 | 0 | 9629 | 0 | 0 | 64613 | 64613 | 0 | 100 | 0 | No | 131548 |  | Yes | 0 | 66935 | 615
H | 37 | 57 | TR-0057-2024-0016 | U.S. Fish & Wildlife Service | Aircraft | 1968 | 2008 | 256 | 49 | 2 | 307 | 0 | 0 | 32280 | 32280 | 0 | 100 | 0 |  | 32501 |  | yes | 2078 | 228 | 190
C | 14 | 57 | TR-0057-2024-0016 | Scientific Committee on Antarctic Research | Aircraft | 1940 | 2000 | 0 | 0 | 550 | 550 | 0 | 5970 | 326925 | 326925 | 0 | 100 | 0 |  | 346043 |  | Yes | 254794 | 16633 | 2
P | 21 | 57 | TR-0057-2024-0016 | USGS-EROS | Aircraft | 1975 | 1996 | 14 | 0 | 11 | 25 | 0 | 0 | 2096 | 2096 | 0 | 100 | 0 |  | 2139 |  | yes | 1893 | 43 | 14
E | 24 | 57 | TR-0057-2024-0016 | USGS - South Dakota State University | Aircraft | 1971 | 1972 | 1 | 1 | 1 | 3 | 0 | 0 | 88 | 88 | 0 | 100 | 0 |  | 88 |  |  | 66 | 0 | 1
M | 53 | 57 | TR-0057-2024-0059 | USGS McDonnell Douglas | Aircraft | 1956 | 1975 | 851 | 4 | 2 | 857 | 0 | 0 | 191275 | 26674 | 164601 | 13 | 23 |  | 95759 |  |  | 28061 | 92 | 0 |  |  |  |  | Data entry and scanning are in progress.
U | 89 | 57 | TR-0057-2024-0016 | Urban Area | Aircraft | 2001 | 2010 | 559 | 18 | 0 | 577 | 0 | 0 | 91304 | 91304 | 0 | 100 | 0 |  | 93457 |  | Yes | 86388 | 2153 | 561
1 | 54 | 57 | TR-0057-2024-0092 | North American Glacier Aerial Photography | Aircraft | 1951 | 2001 | 1032 | 4 | 1 | 1037 | 0 | 0 | 94545 | 94545 | 0 | 100 | 0 |  | 95927 |  | Yes | 2034 | 1382 | 54 |  |  |  |  | Center point geo-referencing updates are ongoing.
1 | 1 | 57 | TR-0057-2024-0059 | National High Altitude Photography | Aircraft | 1980 | 1989 | 2898 | 34 | 3 | 2935 | 0 | 0 | 511039 | 306503 | 204536 | 59.9764 |  |  | 563650 | Yes | Yes | 482523 | 52611 | 1719 |  |  |  |  | NHAP CIR - No dupes exist. EROS has the Originals. NHAP B&W = mixed Ownership. APFO has half of the originals and EROS has the other. Only CIR rolls have been scanned at High Resolution. # of original CIR Rolls (dupes have already been pulled) 1,685 and 1,213 original B&W = 2,898 (Column I) 34 rolls of dupe NHAPOK (Which is our only copy) # of B&W dupes: approximately 1,213 (cans next to originals on the shelf, but no record in the database)
1 | 2 | 57 | TR-0057-2024-0059 | National Aerial Photography Program | Aircraft | 1987 | 2007 | 4324 | 4741 | 1221 | 10286 | 0 | 0 | 1384972 | 31875 | 1353097 | 2.3015 | 301 |  | 1400307 | Yes | Yes | 1391839 | 15335 | 3679 |  |  |  |  | 859 rolls of NAPP Originals remain at EROS & have not been scanned (APFO is scanning them) # of Original CIR rolls: 859 and # of Original BW Rolls: 3,465 = 4,324 (Column I) # of CIR Dupes 2,890 (2,820 2nd gen 'orig' + 70 excess rolls) # of BW dupes: 3,072 (1,921 2nd gen 'orig' + 1,151 excess rolls) (2,820 + 1,921 = 4,741 – Column J)
8 |  |  | TR-0057-2024-0058 | Landsat MSS 70 mm black & white rolls (NSLRSDA) | Satellite | 1972 | 1979 |  |  |  | 7070 | 0 | 0 | 1256556 | 456 | 1256100 | 0.03629 | 167 |  | 1256556 | Yes | No | 1256556 | 0 | 0 |  |  |  |  | The Landsat 70mm collection is made up of three types of rolls. The N-2 are considered our working master that EROS received from Goddard. From the N-2 (Negative 2nd generation) we made a P-3 copy (Positive 3rd Generation) and from the P-3 we made an N-4 (Negative 4th Generation)
8 |  |  |  | Canadian Landsat 70 mm (NSLRSDA) | Satellite | 1972 | 1979 |  |  |  | 6892 | 0 | 0 |  |  | 0 |  | ? | No | Yes | Yes | No | Yes |  | 0 |  |  |  |  | Canada Film : 423,543 MSS, 105,964 TM
8 |  |  | TR-0057-2024-0058 | Landsat MSS 9-inch (NSLRSDA) (Chips) | Satellite | 1972 | 1979 |  |  |  | 2693 | 0 | 0 | 31560 | 36 | 31524 | 0.11407 | 21 |  | 31560 | Yes | No | 31560 | 0 | 0
8 |  |  | TR-0057-2024-0058 | Landsat TM 9-inch (NSLRSDA) (Chips) | Satellite | 1982 | 1992 |  |  |  | 713 | 0 | 0 | 11011 | 8302 | 2709 | 75.3973 | 2 |  | 11011 | Yes | No | 11011 | 0 | 0 |  |  |  |  | This is a film copy that EROS does not have either a good digital file for or no digital file
8 |  |  | TR-0057-2024-0058 | Landsat RBV 70-mm (NSLRSDA) | Satellite | 1978 | 1983 |  |  |  | 616 | 0 | 0 | 81142 | 16 | 81126 | 0.019719 | 11 |  | 81142 | Yes | No | 81142 | 0 | 0
8 |  |  |  | Landsat RBV 9-inch (NSLRSDA) (Chips) | Satellite | 1978 | 1983 |  |  |  | 712 | 0 | 0 | 56849 | 62 | 56787 | 0.10906 | 38 |  | 56849 | Yes | No | 56849 | 0 | 0
A | 11 | 18 |  | Army Map Service | Aircraft | 1941 | 1976 | 1743 | 27 | 105 | 1875 | 0 | 0 | 209224 | 206924 | 2300 | 98.9007 | 2 |  | 230952 |  |  | 147615 | 21116 | 0
B | 12 | 18 |  | Air Force | Aircraft | 1940 | 1993 | 2880 | 44 | 183 | 3107 | 0 | 0 | 262663 | 237855 | 24808 | 90.5552 | 17 |  | 265532 |  |  | 165237 | 24431 | 816
C | 13 | 80 |  | Navy | Aircraft | 1945 | 1973 | 1058 | 8 | 12 | 1078 | 0 | 0 | 133771 | 125747 | 8024 | 94.0017 | 1 |  | 139498 |  |  | 78117 | 9792 | 6
N | 25 | 77 |  | Corps of Engineers | Aircraft | 1969 | 1989 | 96 | 100 | 45 | 241 | 0 | 0 | 25136 | 6537 | 18599 | 26.0065 | 8 |  | 25951 |  | Yes | 22682 | 798 | 61
Z | 46 | 311 |  | Hazards | Aircraft | 1946 | 2002 | 160 | 75 | 2 | 237 | 0 | 0 | 28599 | 8437 | 20162 | 29.501 | 13 |  | 20857 |  |  | 20337 | 339 | 35
J | 45 | 311 |  | Federal Emergency Management Agency | Aircraft | 1999 | 2004 | 32 | 0 | 0 | 32 | 0 | 0 | 459 | 459 | 0 | 100 | 0 |  | 488 |  |  | 459 | 29 | 1
L | 20 | 79 | TR-0079-2023-0154 | National Park Service | Aircraft | 1957 | 2006 | 0 | 0 | 9 | 9 | 0 | 533 | 47041 | 47041 | 0 | 100 | 0 |  | 55296 |  |  | 41448 | 2147 | 0 |  | Yes |  | 83/3
L | 60 | 79 |  | National Park Service - Alaska | Aircraft | 1978 | 2012 | 1444 | 28 | 9 | 1481 | 0 | 0 | 23481 | 23481 | 0 | 100 | 0 |  | 25286 |  |  | 0 | 1805 | 1096
2 | 5 | 115 | TR-0115-2024-0012 | Bureau of Reclamation | Aircraft | 1939 | 2003 | 0 | 0 | 10 | 10 | 0 | 3124 | 142981 | 142981 | 0 | 100 | 0 |  | 164063 |  |  | 82020 | 20811 | 0 |  | Yes |  | 226/9 | 9 Pallets shipped to College Park, MD; April, 2026
7 | 27 | 255 |  | Large Format Camera | Satellite | 1984 | 1984 | 8 | 0 | 8 | 16 | 0 | 0 | 2139 | 2139 | 0 | 100 | 0 |  | 2139 |  | Yes | 2134 | 0 | 2
7 | 30 | 255 |  | Gemini | Satellite | 1965 | 1966 | 0 | 45 | 32 | 77 | 0 | 0 | 2447 | 0 | 2447 | 0 | 1 |  | 2626 |  |  | 54 | 177 | 45
G | 31 | 255 |  | Skylab | Satellite | 1973 | 1974 | 0 | 619 | 400 | 1019 | 0 | 0 | 50486 | 1467 | 49019 | 2.9058 | 22 |  | 38765 |  |  | 38765 | 0 | 200
9 | 10 | 255 |  | USGS - NASA/ERIM Helicopter | Aircraft | 1974 | 1982 | 0 | 412 | 0 | 412 | 0 | 0 | 41200 | 0 | 41200 | 0 | 5 |  | 0 |  | Yes | 0 | 0 | 412
5 | 8 | 255 |  | NASA/Ames Research Center | Aircraft | 1971 | 2002 | 2939 | 1718 | 2595 | 7252 | 0 | 0 | 554699 | 37689 | 517010 | 6.7945 | 115 |  | 569857 | Yes | Yes | 567568 | 1051 | 3059 |  |  |  |  | 312 original rolls left to scan (26,612 frames) 17,714 original frames already scanned.
5 | 38 | 255 |  | Ames Alaska High Altitude Photography | Aircraft | 1976 | 1986 | 0 | 221 | 48 | 269 | 0 | 0 | 43178 | 43178 | 0 | 100 | 0 |  | 43399 | Yes | Yes | 43125 | 221 | 113
6 | 9 | 255 |  | NASA/Johnson Space Center | Aircraft | 1965 | 1983 | 4899 | 2653 | 3544 | 11096 | 0 | 0 | 1153255 | 251888 | 901367 | 21.8415 | 200 |  | 390351 | Yes | Yes | 313240 | 2369 | 3913
6 | 39 | 255 |  | Johnson Alaska High Altitude Photography | Aircraft | 1977 | 1980 | 13 | 80 | 12 | 105 | 0 | 0 | 19278 | 19278 | 0 | 100 | 0 |  | 19504 | Yes | Yes | 17846 | 226 | 60
D | 15 | 255 |  | NASA/Wallops Island | Aircraft | 1970 | 1977 | 15 | 812 | 4 | 831 | 0 | 0 | 65443 | 48971 | 16472 | 74.83 | 7 |  | 63827 | Yes | Yes | 63438 | 231 | 531
F | 16 | 255 |  | NASA/Kennedy | Aircraft | 1972 | 1976 | 1 | 224 | 1 | 226 | 0 | 0 | 13247 | 314 | 12933 | 2.3703 | 3 |  | 314 | Yes | Yes | 0 | 0 | 133
I | 18 | 255 |  | NASA/Stennis | Aircraft | 1973 | 2003 | 1 | 1 | 0 | 2 | 0 | 0 | 467 | 0 | 467 | 0 | 0 |  | 469 | Yes | Yes | 298 | 2 | 2
R | 22 | 255 | TR-0255-2024-0148 | NASA/Marshall Space Flight Center | Aircraft | 1972 | 1977 | 0 | 0 | 0 | 0 | 0 | 41 | 7923 | 132 | 7791 | 1.666 | 2 |  | 3910 | Yes | Yes | 3910 | 0 | 0 |  | Yes |  | 10/0 | 10 Boxes shipped to College Park, MD; 2/27/2026
|  |  |  | CA Earthquake Film | Aircraft |  |  | 25 |  |  | 25 | 0 | 0 | [8 empty] | No
|  |  |  | Declassification I (CORONA, ARGON, LANYARD) (NSLRSDA) | Satellite | 1960 | 1972 | 0 | 13343 |  | 13343 | 0 | 0 | 945570 | 39536 | 906034 | 4.1812 |  |  | 945570 |  | Yes | 928588 | 0 | 26
|  |  |  | Declassification II (KH-7, KH-9) (NSLRSDA) | Satellite | 1963 | 1980 | 0 | 2008 |  | 2008 | 0 | 0 | 46954 | 5951 | 41003 | 12.6741 |  |  | 46954 |  | Yes | 45601 | 0 | 44
|  |  |  | Declassification III (HEXAGON KH-9) (NSLRSDA) | Satellite | 1971 | 1984 | 0 | 13467 |  | 13467 | 0 | 0 | 602661 | 21490 | 581171 | 3.5659 |  |  | 602661 |  | Yes | 586113 | 0 | 95 |  |  |  |  | Browse Imagery made on the Phoenix "VI" platform
[11 empty] | 117332 | 0 | 22342 | 11416988 | 5087134 | 6329854